## Sheet1
Timeline for Lowland Canals Outages 2018 | [11 empty] | Timeline for Lowland Canals Outages 2019 | [11 empty] | Timeline for Lowland Canals Outages 2020 | [11 empty] | Timeline for Lowland Canals Outages 2021
Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
| Bonnybridge and Twechar Bridges closed to navigation | [15 empty] | Lock 34 |  |  |  | Garscube Bridge Works ( Covid restrictions applied)
[7 empty] | Lock 6 closed navigation to Kelpies | [14 empty] | Falkirk |  |  | Wilcox Homes work Linlithgow Section stop planks in place
[22 empty] | Tunnel |  |  | Covid restrictions applied
[8 empty] | Leamingtom Bridge closed | [13 empty] | Works
[26 empty] | Bowling Sealock Closed for repairs | [7 empty] | Falkirk
[10 empty] | Linlithgow Works | [15 empty] | Covid restrictions applied | [7 empty] | Wheel
Works
Union Canal Breach ( Covid restrictions applied)
Maryhill to Bowling closed due to Covid restrictions
Stockingfield Canal BrIdge Closure
(Covid restrictions applied)
Key
F&C canal
Union canal
Both canals
Capital Projects
Breakdowns